## Overview
Baja SAE 2025-2026
Name | #
Total Cost: | 2386.7041
Already Purchased | 0
Still to be Purchased | 0
Total Car Weight | #REF!
Total # of Parts on car | #REF!
Total # of Spare Parts | #REF!
|  |  | Driver Weight: | 170 | lbs
Progress Report
Column1 | Column2
Overall | 0%
Drivetrain | 0%
Chassis | 0%
Driver controls | 0%
Suspension | 0%
Subsystem | Cost Without Spares | Total Cost |  | Subsystem | Total Weight LB | Subsystem | Weight Saved LB
Drivetrain | 5189.91 | 5224.09 |  | Drivetrain | 198.81 | Carla Weight | 552
Chassis | 1394.24 | 1844.24 |  | Chassis | 94.94 | Drivetrain | 12.49
Suspension | 2649.02 | 2658.97 |  | Suspension | 130.2683 | Chassis | 32.3
Driver Controls | 2114.37 | 2292.55 |  | Driver Controls | 30.29 | Suspension | 36.41
Total | 11347.54 | 12019.85 |  | Tabs | 20 | Driver Controls | 12.14
|  |  |  | Total | 474.3083 | Total | 458.66

## Gantt
Key: | Completed | Working on | Not Started | Past Week | Current week | % complete per subsystem
| Prelimary Design | Final Design
| Part Ordered | Parts Manufactured
| Part Assembled | Part Complete
[10 empty] | PDR | FDR | Parts Ordered |  |  |  | Weld Chassis | [5 empty] | Rolling Chassis | [5 empty] | Drivable Veh. |  |  | Rule Compliant |  | Testing
Subsystem | Component | Part Name | Importance | % Complete Final Design | % Complete Manufactured | % Complete on car | Owner | NOTES: | 29-Oct | 9-Nov | 12-Nov | 17-Nov | 27-Nov | 4-Dec | 11-Dec | 18-Dec | 25-Dec | 1-Jan | 8-Jan | 15-Jan | 22-Jan | 29-Jan | 5-Feb | 12-Feb | 19-Feb | 26-Feb | 4-Mar | 11-Mar | 18-Mar | 25-Mar | 1-Apr | 8-Apr | 15-Apr | 22-Apr | 29-Apr | 6-May | 13-May | 17-May
Drivetrain
| D.1 | Engine |  | 100% | 0% |  |  |  |  | x | x |  |  | x | [5 empty] | x | x
| D.1.1 | Restrictor Plate |  | 0% | [5 empty] | x | x |  |  | x | [5 empty] | x | x
| D.1.2 | Throttle Cable |  | 0% | [5 empty] | x | x | x | [11 empty] | x
| D.1.3 | Accelerator Pedal |  | 0% | [5 empty] | x | x | x | [11 empty] | x
| D.1.4 | Fuel system | [7 empty] | x | x | x | [11 empty] | x
| D.2.1 | CVT Drive Pully |  | 0% | [5 empty] | x | x | x | [8 empty] | x
| D.2.2 | CVT Driven Pully |  | 0% | [5 empty] | x | x | x | [8 empty] | x
| D.2.3 | CVT Guard |  | 0% | [5 empty] | x | x | x | [12 empty] | x
| D.3 | Rear Drive |  | 0% | [5 empty] | x | x | x | [7 empty] | x | x
| D.4 | Driveshaft |  | 0% | [5 empty] | x | x | x | [7 empty] | x | x
| D.4.2 | Driveshaft Guard |  | 0% | [5 empty] | x | x | x | [10 empty] | x
| D.5 | Front Drive |  | 0% | [5 empty] | x | x | x | [8 empty] | x
| D.6 | Rear CV Axles |  | 0% | [5 empty] | x | x | x | [12 empty] | x | x
| D.6.1 | Front CV Axle |  | 0% | [5 empty] | x | x | x | [12 empty] | x | x
Driver Controls
| DC.1 | Steering |  | 0% | [5 empty] | x | x | x
| DC.1.1 | Tie Rods |  | 0% | [5 empty] | x | x | x |  |  | x
| DC.1.2 | Rack & Pinion |  | 0% | [5 empty] | x | x | x |  |  | x
| DC.1.3 | Steering Column |  | 0% | [5 empty] | x | x | x |  |  | x
| DC.1.4 | Steering Wheel |  | 0% | [5 empty] | x | x | x | [8 empty] | x
| DC.2 | Brakes |  | 0% | [5 empty] | x | x | x
| DC.2.1 | Master Cylinder |  | 0% | [5 empty] | x | x | x |  |  | x
| DC.2.2 | Brake Lines |  | 0% | [5 empty] | x | x | x | [12 empty] | x | x | x
| DC.2.3 | Front Rotors |  | 0% | [5 empty] | x | x | x | [8 empty] | x
| DC.2.4 | Front Calipers |  | 0% | [5 empty] | x | x | x
| DC.2.5 | Rear Rotors |  | 0% | [5 empty] | x | x | x | [8 empty] | x
| DC.2.6 | Rear Calipers |  | 0% | [5 empty] | x | x | x
| DC.3 | Electrical |  | 0% | [5 empty] | x | x | x
| DC.3.1 | Benchtop | [7 empty] | x | x | x |  |  | x | [6 empty] | x
| DC.3.2 | Kill Switches |  | 0% | [5 empty] | x | x | x | [11 empty] | x |  |  |  | x
| DC.3.3 | Brake light |  | 0% | [5 empty] | x | x | x | [11 empty] | x |  |  |  | x
| DC.3.4 | Reverse Light |  | 0% | [5 empty] | x | x | x | [11 empty] | x |  |  |  | x
| DC.3.5 | Reverse Alarm | [7 empty] | x | x | x | [11 empty] | x |  |  |  | x
| DC.4 | Safety |  | 0% | [5 empty] | x | x | x
| DC.4.1 | Harness |  | 0% | [5 empty] | x | x | x | x | [11 empty] | x |  | x
| DC.4.2 | Arm Restraints |  | 0% | [5 empty] | x | x | x | x
| DC.4.3 | Helmet |  | 0% | [5 empty] | x | x | x | x
| DC.4.4 | Fire Suit |  | 0% | [5 empty] | x | x | x | x
Chassis
| C.1 | Frame |  | 0% | [5 empty] | x |  | x | x | x | x
| C.2 | Body Panel |  | 0% | [5 empty] | x | x | x |  |  | x
| C.2.1 | Side Body Panel |  | 0% | [5 empty] | x | x | x |  |  | x | [6 empty] | x | x | x | x
| C.2.2 | Nose Plate |  | 0% | [5 empty] | x | x | x |  |  | x | [6 empty] | x | x | x | x
| C.2.3 | Nose Skid Plate |  | 0% | [5 empty] | x | x | x |  |  | x | [6 empty] | x | x | x | x
| C.2.4 | Skid Plate |  | 0% | [5 empty] | x | x | x |  | x | x | [6 empty] | x | x | x | x
| C.2.5 | Paint |  | 0% | [5 empty] | x | x | x | [14 empty] | x |  |  |  | x | x
| C.3 | Ergonomics |  | 0% | [5 empty] | x | x | x
| C.3.1 | Seat |  | 0% | [5 empty] | x |  | x | x | x | x | [5 empty] | x | x
| C.3.2 | Steering Wheel Position |  | 0% | [5 empty] | x | x | x |  |  | x | x | [5 empty] | x
| C.3.3 | Gas Pedal Position |  | 0% | [5 empty] | x | x | x |  |  | x | x | [5 empty] | x
| C.3.4 | Brake Pedal Position |  | 0% | [5 empty] | x | x | x |  |  | x | x | [5 empty] | x
| C.3.5 | Seat Cushion | [7 empty] | x | x | x |  | x | x | x |  |  |  |  | x | x
| C.4 | Firewall |  | 0% | [5 empty] | x | x | x |  |  | x | x |  |  |  |  | x | x | x
| C.4.1 | Firewall Plate |  | 0% | [5 empty] | x | x | x |  |  |  | x |  |  |  |  | x | x | x
| C.4.2 | Seat Belt Covers |  | 0% | [5 empty] | x | x | x |  |  |  | x |  |  |  |  | x | x | x
| C.5 | Mounts |  | 0% | [5 empty] | x | x | x
| C.5.1 | Engine Mounts |  | 0% | [5 empty] | x | x | x | [8 empty] | x | x
| C.5.2 | Differential Mounts |  | 0% | [5 empty] | x | x | x | [8 empty] | x | x
| C.5.3 | Shock Mounts |  | 0% | [5 empty] | x | x | x |  | x | x | x |  |  |  |  | x | x
| C.5.4 | Seat Mounts |  | 0% | [5 empty] | x | x | x |  | x | x | [5 empty] | x | x
Suspension
| S.1 | Front Suspension Arms |  | 0% | [5 empty] | x | x | x | x | x | x | x |  |  |  | x
| S.1.1 | Upper A-arm |  | 0% | [5 empty] | x | x | x | x | x | x | x |  |  |  | x
| S.1.2 | Lower A-arm |  | 0% | [5 empty] | x | x | x | x | x | x | x |  |  |  | x
| S.1.3 | Front Shocks |  | 0% | [5 empty] | x | x | x |  |  | x | x |  |  |  | x
| S.2 | Swing Arm |  | 0% | [5 empty] | x | x | x |  |  | x | x |  |  |  | x
| S.2.1 | Parallel Arms |  | 0% | [5 empty] | x | x | x |  |  | x | x |  |  |  | x
| S.2.1.1 | Bungs |  | 0% | [5 empty] | x | x | x |  |  | x | x |  |  |  | x
| S.2.1.2 | Ball Joints |  | 0% | [5 empty] | x | x | x |  |  | x | x |  |  |  | x
| S.2.2 | Rear Shocks |  | 0% | [5 empty] | x | x | x |  |  | x | x |  |  |  | x
| S.3.1 | Front Knuckle | [17 empty] | x | x | x
| S.3.2 | Rear Knuckle |  | 0% | [5 empty] | x | x | x | [7 empty] | x | x | x
| S.4 | Wheels |  | 0% | [5 empty] | x | x | x | [9 empty] | x
| S.4.1 | Hubs | [7 empty] | x | x | x | [8 empty] | x | x
| S.4.1.1 | Front Hubs | [7 empty] | x | x | x | [8 empty] | x | x
| S.4.1.2 | Rear Hubs | [7 empty] | x | x | x | [8 empty] | x | x
| S.4.2 | Rims | [7 empty] | x | x | x | x | [6 empty] | x |  | x
| S.4.2.1 | Front Rims | [7 empty] | x | x | x | x | [6 empty] | x |  | x
| S.4.2.2 | Rear Rims | [7 empty] | x | x | x | x | [6 empty] | x |  | x
| S.4.3 | Tires | [7 empty] | x | x | x | x | [6 empty] | x |  | x
| S.4.3.1 | Front Tires | [7 empty] | x | x |  | x | [6 empty] | x |  | x
| S.4.3.2 | Rear Tires | [7 empty] | x | x | [8 empty] | x |  | x

## Drivetrain
Add Parts Under each componente by adding a .X to it | [12 empty] | Paste A link here as link
Total overall Cost: | 5224.09 | Total Weight (lb): | 422.874 | # of Parts on Car: | 205.326
Total Cost Sub donations | 4327.45
without spare parts | 5189.91
# | Part Name | Owner | Design Effort (Low, Med, High) | QTY Nessary for Car | General Description | Same as (# that is the same part) | Fabricate or Off the Shelf | Material | Mass per Part (lb) | Mass Total (lb) On Car | Supplier | Part # | Link | Price/part | # of Spare Parts | Parts Per Package | # of Packages or Parts | # of Spare Parts or Packages | Total # of Parts or Packages to Order | Price per Package or Part | Shipping Cost | Cost Without Spare Parts | Total Cost | Ordered | Received
Will fill in # last | Engine | Josiah Farinacci, Zach Sun | low | 1 | Provides power to the driveline. Must buy Kohler ch440. Weight is estimated will update later | N/A | off shelf | aluminum | 72.1 | 72.1 | Kohler | CH440-3302 | Engine from last year | 477 | 0 | 1 | 1 | 0 | 1 | 476.91 | 225 | 701.91 | 701.91
| Fuel tank, cap, and fitting | Josiah Farinacci, Zach Sun | low | 1 | Holds 1 gallon of fuel. In stock at hudgins | N/A | off shelf | aluminum | 5.2 | 5.2 | Pyrotect | SFC1000 | Pyrotect fuel tank, pickup, and cap (call to order/website down until next week. Backorder: 1 month.) | 350 | 0 | 1 | 1 | 0 | 1 | 350 | 0 | 350 | 350
| Fuel line | Josiah Farinacci, Zach Sun | low | 1 | Rules require 3/16 line. Ordering 4 ft will have extra | N/A | off shelf | rubber | 0.73 | 0.73 | Auto zone | 50054 | Fuel line | 9.98 | 0 | 1 | 1 | 0 | 1 | 9.96 | 0 | 9.96 | 9.96
| Fuel cutoff | Josiah Farinacci, Zach Sun | Low | 1 | Cut off fuel flow from tank | N/A | off shelf | plastic | 0.09 | 0.09 | Amazon-yamakato | AYMK067 | Fuel cutoff | 7.99 | 0 | 1 | 1 | 0 | 1 | 7.99 | 0 | 7.99 | 7.99
| Fuel filter | Josiah Farinacci, Zach Sun | low | 1 | Filter the fuel feeding the engine. must use kohler part | N/A | Off the shelf | Plastic | 0.02 | 0.02 | Amazon (kohler) | B0021Y2XQM | https://www.amazon.com/25-050-21-S1-16-Inch-Diameter/dp/B0021Y2XQM/ref=sr_1_5?adgrpid=1338106223623655&hvadid=83631877562756&hvbmt=be&hvdev=c&hvlocphy=86459&hvnetw=o&hvqmt=e&hvtargid=kwd-83632001867652%3Aloc-190&hydadcr=18707_13465085&keywords=3%2F16%E2%80%9D+fuel+filter&qid=1698789067&sr=8-5 | 10.03 | 0 | 1 | 1 | 0 | 1 | 8.87 | 0 | 8.87 | 8.87
| splash guard | Josiah Farinacci, Zach Sun | med | 1 | manufactured | N/A | Fabricated | aluminum | 1.5 | 1.5 | mcmaster | 89015K143 | Splash guard | 28.44 | 0 | 1 | 1 | 0 | 1 | 41.09 | 0 | 41.09 | 41.09
| CVT Drive Pully | Rachel Morak | low | 1 | sends power from the drive shaft to the driven pulley, 1 in. bore. Estimated weight | N/A | off shelf | Aluminium | 6.4 | 6.4 | Belt Palace | 302405-A | Drive pulley | 269.78 | 0 | 1 | 1 | 0 | 1 | 269.78 | 18.05 | 287.83 | 287.83
| CVT Driven Pully | Rachel Morak | low | 1 | transfers power into the rear diff, 7/8 in. bore. Estimated weight | N/A | off shelf | Aluminium | 8.7 | 8.7 | Belt Palace | 301940A | Driven pulley | 229.78 | 0 | 1 | 1 | 0 | 1 | 229.78 | 0 | 229.78 | 229.78
| CVT Belt |  | low | 1 | connects the drive and driven pulleys 39.12" length | N/A | off shelf | belt | 1 | 1 | Belt Palace | 300634 | drive belt | 57.78 | 1 | 1 | 1 | 1 | 2 | 57.78 | 0 | 57.78 | 115.56
| Draw Latch for Guard | Rachel Morak | low | 2 | allows the guard to open and close easily | N/A | off shelf | stainless steel | 0.05 | 0.1 | Lee Valley | 00S5590 | https://www.leevalley.com/en-us/shop/hardware/latches/draw/48576-stainless-steel-draw-latch?item=00S5590 | 5.9 | 0 | 1 | 6 | 0 | 2 | 5.9 | 10 | 45.4 | 21.8
| CVT Guard | Rachel Morak | high | 1 | HROE guard in compliance with BAJA rules, choose 24" x 48" x .125" option | N/A | Fabricate | 6061-T6 Aluminum | 6.7 | 6.7 | online metals | 1246 | sheet metal | 158.66 | 0 | 1 | 1 | 0 | 1 | 158.66 | 9.28 | 167.94 | 167.94
| Schafer differential | Rachel Morak | med | 1 | transfers power to rear wheels from CVT. Purchase from Landmaster | N/A | off shelf | aluminum | 37.5 | 37.5 | Schafer | 18058 | Rear diff | 1299.99 | 0 | 1 | 1 | 0 | 1 | 1299.99 | 0 | 1299.99 | 1299.99
| Gear shifter cable | Joel Tibbits | med | 1 | 36" control cable | Same as FWD shifter cable | off shelf | steel | 0.75 | 4 | ProWerks | C93-036 | gear shift | 57.94 | 0 | 1 | 1 | 0 | 1 | 57.94 | 0 | 57.94 | 57.94
| Diff lock shifter cable | Joel Tibbits | med | 1 | 54" control cable | N/A | off shelf | steel | 1.1 | 0.2 | ProWerks | C93-054 | gear shift | 62.69 | 0 | 1 | 1 | 0 | 1 | 62.69 |  | 62.69 | 62.69
| Shifter cable ends | Joel Tibbits | low | 4 | Used to attach the cable to the lever need 2 per shifter | N/A | off shelf | steel | 0.01 | 0.01 | ProWerks | C73-380 | Cable ends | 13.99 | 0 | 1 | 6 | 0 | 6 | 13.99 |  | 83.94 | 83.94 |  |  | 282.51
| Shifter cable clamps | Joel Tibbits | low | 4 | used to secure the cable housing need 2 per shifter | N/A | off shelf | steel | 0.01 | 0.01 | ProWerks | C73-375 | Clamps | 12.99 | 0 | 1 | 6 | 0 | 6 | 12.99 |  | 77.94 | 77.94
| Shifter lever assembly and mounts | Joel Tibbits | high | 2 | Will waterjet and bend all parts | N/A | fabricate | steel | 0.7 | 1.4 | online metals |  | sheet metal | 64.88
| Right angle gearbox | Daniel Truxel | med | 1 | mounts right angle gearbox to diff | n/A | fab | 6061 aluminum | 2.025 | 2.025 | online metals | mp-00000311 | mounting plate | 52.89 | 0 | 1 | 1 | 0 | 1 | 52.89 | 0 | 52.89 | 52.89 |  |  |  | Part Name | Quantity | Weight on car (lb) | Total Cost | Part Name | Quantity | Assumed weight (lb) | Total Cost
already have | Output shaft | Daniel Truxel | high | 1 | Connects to output gear and driveshaft. Have some at hudgins, enough to make 2 | CV axle extension | fab | 4340 steel Alloy | 1.09 | 1.09 | Mcmaster | 4437T14 | Same as driveshaft extension | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | in stock at hudgins | in stock at hudgins |  | Right angle gearbox mounting plate | 1 | 1.5 | 52.89 | 18081 Right Angle Gear Box | 1 | 7 | 449.99
| Miter gears | Daniel Truxel | low | 2 | Input slides onto 4wd shaft on diff, output gear slides onto uotput shaft | N/A | off shelf | 1144 carbon steel | 1.6 | 3.2 | Mcmaster | 6843K19 | Miter gear | 91.88 | 0 | 1 | 2 | 0 | 2 | 91.88 | 0 | 183.76 | 183.76 |  |  |  | Bearing housings | 2 | 1 | 19.72 | 19887 KIT, 4 Jaw Coupler MY21 | 1 | 1.2 | 149.99
| snap ring | Daniel Truxel | low | 2 | secures output shaft and gear | N/A | off shelf | hardened steel | 0.001 | 0.002 | amazon | 50458A | snap ring kit | 9.97 | 0 | 300 | 1 | 0 | 1 | 9.97 | 0 | 9.97 | 9.97 |  |  |  | Right angle gearbox side, top and bottom | 3 | 1.5 | 14.11 | Totals: |  | 8.2 | 599.98
| Gasket/seal | Daniel Truxel | low | 1 | gasket maker for gear box | N/A | off shelf | silicone | 0.01 | 0.01 | amazon | ‎82180 | gasket maker | 5.98 | 0 | 1 | 1 | 0 | 1 | 5.98 | 0 | 5.98 | 5.98 |  |  |  | Output shaft | 1 | 1.3 | 0
| bearings | Daniel Truxel | low | 2 | supports output shaft | N/A | off shelf | hardened steel | 0.01 | 0.02 | amazon | B08HR2JNGJ | Bearings | 9.95 | 0 | 4 | 1 | 0 | 1 | 9.95 | 0 | 9.95 | 9.95 |  |  |  | Miter gears | 2 | 2 | 183.76
| Gearbox latch | Joel Tibbits | low | 1 | Secure 90 degree gearbox lid | N/A | off-shelf | Zinc-plated steel | 0.09 |  |  |  | Draw latch | 7.37 | [5 empty] | 7.37 |  | 7.37 | 7.37 |  |  |  | snap ring | 2 | 0.002 | 9.97
| Gear oil rear diff/gearbox | [7 empty] | 0.05 | 0.05 | amazon | ‎773732 | Gear oil | 28 | 0 | 1 | 1 | 0 | 1 | 28 |  | 28 | 28 |  |  |  | Gasket/seal | 1 | 0.01 | 5.98
| Driveshaft | Zach Altland | Low | 1 | Solid 7075 round bar, 1 Inch diameter, 48 inch length | N/A | Off shelf | 7075-T6 Aluminum | 2.8 | 2.8 | Midwest Steel |  | Driveshaft | 68.98 | 0 | 1 | 1 | 0 | 1 | 68.98 | 0 | 68.98 | 68.98 |  |  |  | Gear oil rear diff/gearbox |  | 0.05 | 28
| Double 1" U-Joint | Zach Altland | med | 1 | Connects the driveshaft to the front diff. Double D connection with 1" ID ends | N/A | off the shelf | 7075 Aluminum | 1 | 1 | Borgeson | 215252 | 1" U-joint | 89.55 | 0 | 1 | 1 | 0 | 1 | 89.55 |  | 89.55 | 89.55 |  |  |  | Totals: |  | 7.362 | 314.43
| 1" & 3/4" Ujoint | Zach Altland | med | 1 | Connects the driveshaft to the gear box. Double D connection with 1" ID on one and 3/4" other end | N/A | Off the shelf | 7075 Aluminum | 1 | 1 | Borgeson | 214952 | 3/4" and 1" U-joint | 89.55 | 0 | 1 | 1 | 0 | 1 | 89.55 |  | 89.55 | 89.55
| Powertrain Guard | Zach Altland | Med | 2 | Guards the drive shaft, chose 12" X 18" option | N/A | Fabricate | 6061 - T6 Aluminum | 2.73 | 4.76 | online metals | mp-00000277 | Driveshaft Guard | 86.2 | 0 | 1 | 2 | 0 | 2 | 86.2 |  | 172.4 | 172.4 |  |  | 218.14
| Finger protection guard | Zach Altland | Med | 1 | Guards the drive shaft, select a size - enter 10 inches for the width and 40 inches for the length | N/A | Fabricate | 6062 - T6 Aluminum | 2 | 1 | online metals | 13493 | Finger Protection Guard | 45.74 | 0 | 1 | 1 | 0 | 1 | 45.74 |  | 45.74 | 45.74
| Rear CV axle couplers | Daniel Truxel | high | 2 | adapts from cv axle to differential male splines. 1' ordered | N/A | Fabricated | 4340 | 0.3 | 0.6 | mcmaster | 4437T17 | 1.5" round stock | 58.8 | 0 | 1 | 1 | 0 | 1 | 58.8 | 0 | 58.8 | 58.8
| Front differential swtich | Gabe Womack | low | 1 | Switch to lock front diff | N/A | off shelf | plastic | 0.02 | 0.02 | amazon | ‎4350151996 | Front diff swtich | 9.99 | 0 | 1 | 1 | 0 | 1 | 9.99 | 0 | 9.99 | 9.99
| Front Differential | Aiden Ortiz | Med | 1 | Transers power to the front wheels | N/A | Off the shelf, extended | Cast Aluminium | 15.7 | 15.7 | east lake axle | DIFF301.01 | front diff | 300 | 0 | 1 | 1 | 0 | 1 | 300 |  | 300 | 300
| Rear Right CV axle | Zachary Dickinson | low | 1 | Transfers power from differentials to wheels. Got 4 for free, paid for two extras | N/A | Off the shelf | 4340 steel | 10.8 | 10.8 | Landmaster | 18045 Shaft, CV RR 56 | 18045 Shaft, CV RR 56 - Landmaster | 179.99 | 0 | 1 | 1 | 0 | 1 | 179.99 | 0 | 179.99 | 179.99
| Rear Left CV axle | Jude Maretzki | low | 1 | Transfers power from the rear differential to the wheels. Sourced from Landmaster | N/A | Off the shelf | 4340 steel Alloy | 10.5 | 10.5 | Landmaster | 18044 Shaft, CV LR 56 | 18044 Shaft, CV LR 56 - Landmaster | 149.99 | 0 | 1 | 1 | 0 | 1 | 149.99 |  | 149.99 | 149.99
| Front CV Axles | Gabriel Womack | med | 4 | Transfers power from differentials to wheels. Got 4 for free, paid for two extras |  | Off the shelf | 4340 steel Alloy | 10 | 10 | East Lake Axle | ‎CASWB337F2B.014 | https://www.amazon.coms/ | 199.99 | 2 |  | 2 | 0 | 4 | 199.99 | 0 | 199.99 | 199.99
order soon | Accelerator Cable | Gabe Womack | Low | 1 | Controls the power of the engine. Must be at least 80" | N/A | Off the shelf | Rubber/aluminium | 0.5 | 0.5 | Amazon WATODAY | H071 | https://www.amazon.com/Throttle-Cable-Enhanced-Casing-Manco/dp/B082XR6SYT/ref=sr_1_26?crid=2IAF6ANNGQXJB&dib=eyJ2IjoiMSJ9.I8tlaBlVyUoro3du1Av5VFjpVV-dIx_wuNg_PizmA3coWH1edMjeklCJA-Vmc8uQoQ6Y1jIc5TmXPc_j0UdhRDNpkV5hhrNn0xUZTOufpzRZXYLFjna0ukatf_28DGairo5y-_H-XeSRR4_7_wiN0TMNC46rsXC8XWO51XZ3WEVWFw3cLNWsxls1rIz4iTLbBGnld4W0dys25DvEpLfuKiJUmN3D9Huu34kiIT06CR4-fXkVD-uqTo1sTD5bj4xOwOzp0bPqwHEGmng-I7zYDCJ8iNMe-KquUz2jF4wKyYw.lRwcwYdxWVF4eAsa1Awlz7fvTuIw7mMjxsQ5UutipfQ&dib_tag=se&keywords=8+ft+throttle+cable&qid=1711034852&sprefix=8+ft+throttle+cable%2Caps%2C81&sr=8-26 | 13.49 | 0 | 1 | 1 | 0 | 1 | 12.99 |  | 12.99 | 12.99
| Accelerator Pedal | Gabe Womack | Low | 1 | allows to driver to control the power opf the engine | N/A | Off the shelf | Aluminium | 0.5 | 0.5 | Amazon yofuxa | JT04-KDC | https://www.amazon.com/YOXUFA-Throttle-Pedals-Springs-Vintage/dp/B0BG9NVJV2/ref=sr_1_12?crid=2DRF9B52BZN19&keywords=carter%2Buniversal%2Bgo%2Bkart%2Bpedal&qid=1701552781&sprefix=carter%2Buniversal%2Bgo%2Bkart%2Bpedal%2Caps%2C63&sr=8-12&th=1 | 14.99 | 0 | 1 | 1 | 0 | 1 | 14.99 |  | 14.99 | 14.99
| Fuel Line Clamps | Gabe Womack | Low | 8 | Clamps the fuel lines so there are no leaks | N/A | Off the shelf | Aluminium | 0.02 | 0.16 | Auto zone | 25184 | https://www.autozone.com/gaskets-and-miscellaneous-fasteners/hose-clamp/p/nitro-4x4-1-4in-5-8in-hose-clamp-4-pack/268441_0_0?searchText=hose+clamps | 3.99 | 0 | 8 | 2 | 0 | 2 | 3.99 |  | 7.98 | 7.98
| Vent tube | Gabe womack, ben scarola | low | 2 | in stock at hudgins vent tube for differentials required by rules | N/A | Off the shelf | rubber | 0.02 | 0.04 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | in stock at hudgins | in stock at hudgins
| Front diff oil | [8 empty] | 211.437 |  |  | https://www.amazon.com/gp/product/B07BYCHTZZ/ref=ox_sc_act_title_1?smid=A25WY1XMKY7USE&psc=1
| key stock | [8 empty] | 0 |  |  | https://www.mcmaster.com/orders/ |  |  |  |  | 0 | 0 |  |  | 0 | 0
| Vent tube | [8 empty] | 0 |  |  | https://www.amazon.com/gp/product/B09QPV578W/ref=ox_sc_act_title_1?smid=A9G01LO7M14IV&psc=1 |  |  |  |  | 0 | 0 |  |  | 0 | 0
| driveshaft | [8 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0

## Cost Breakdown
| 2025 | 2024
Parts | Cost |  | I can finish this if you want to work on other stuff |  |  | u want a pie chart to compare to last year right?
Front Diff | 300 | 300
Shifter | 282.51 | 65.24 | Sure |  |  | yes
Engine | 701.91 | 701.91 |  |  |  | Put it on slide 17 and 18
Fuel system | 376.82 | 376.82
Drive shaft Gaurd | 218.14 | 172.4
Splash Gaurd | 41.09 | 41.09
CVT System | 743.33 | 801.11 |  | CVT (Driving) | 287.83
Rear Diff | 1299.99 | 1299 |  | CVT (Driven) | 229.78
Driveshaft | 300 | 210 |  | CVT Belt | 57.78
90 Dgree Gear Box | 324.38 | 324.38 |  | CVT Gaurd | 167.94
Acelerator Pedal | 28.48 | 27.98
Front CV Axles (2) | 200 | 169.98
Rear CV Axles (2) | 329.98 | 169.98
Total | 5146.63 | 4659.89
486.74

## Chassis
Add Parts Under each componente by adding a .X to it | [12 empty] | Paste A link here as link
Total overall Cost: | 2113.79 | Total Weight (lb): | 94.94 | # of Parts on Car: | 33.27 |  |  |  |  | Mass Total (lb) On Car | [11 empty] | 2113.79
| 1663.79 | [8 empty] | 94.94
# | Part Name | Owner | Design Effort (Low, Med, High) | QTY Nessary for Car | General Description | Same as (# that is the same part) | Fabricate or Off the Shelf | Material | Mass/part (lb) | Mass Total (lb) On Car | Supplier | Part # | Link | # of Spare Parts | Parts Per Package | # of Packages or Parts | # of Spare Parts or Packages | Total # of Parts or Packages to Order | Price per Package or Part | Shipping Cost | Cost Without Spare Parts | Total Cost | Ordered | Received
C.1 | Frame | Harley Cole | High |  |  |  | Fabricate |  |  | 55 | [7 empty] | 0 |  | 347 | 347 | 347
C.1.1 | Primary Members | Harley Cole | High | 1 | 1.25 x 0.065 Tubing |  | Fabricate | 4130 steel |  | 0 | Wicks | R1-1/4X065-41 | link |  |  | 1 |  | 1 | 530.04 |  | 530.04 | 530.04 | Yes
C.1.2 | Secondary Members | Harley Cole | High | 1 | 1 x 0.035 & 1 x 0.049 Tubing |  | Fabricate | 4130 steel |  | 0 | Wicks | R1X035-41 | link |  |  | 1 |  | 1 | 628.68 |  | 628.68 | 628.68 | Yes
C.2 | Body Panels & Skid Plates | [8 empty] | N/A | [7 empty] | 0 |  |  | 0 | 0
C.2.1 | Cockpit Body Panels | Connor Archer | Low | 2 | Protective panel that goes on the side of the car |  | Fabricate | Corrugated plastic | 2.5 | 5 |  |  |  | 0 | 1 | 2 | 0 | 2 |  |  |  | 0 | No
C.2.2.1 | Nose Body Panels (Upper, Side) | Connor Archer | Low | 2 | Protective panel on upper sides of nose |  | Fabricate | Corrugated plastic | 1 | 2 | [7 empty] | 0 |  |  | 0 | 0
C.2.2.2 | Nose Body Panels (Lower, Side) | Connor Archer | Low | 2 | Protective panel on lower sides of nose |  | Fabricate | Corrugated plastic | 1.32 | 2.64 | [7 empty] | 0 |  |  | 0 | 0
C.2.3 | Rear Number Panels | Connor Archer | Low | 2 | Number panels for rear/sides of car |  | Fabricate | Corrugated plastic | 1.04 | 2.08 | [7 empty] | 0 |  |  | 0 | 0
C.2.4 | Rear Numbers | Connor Archer | Low | 2 | Numbers for rear/sides of car |  | Fabricate | 3d printed plastic (ABS) | 0.81 | 1.62 | [7 empty] | 0 |  |  | 0 | 0
C.2.5 | Front Numbers | Connor Archer | Low | 1 | Numbers for front of car |  | Fabricate | 3d printed plastic (ABS) | 0.81 | 0.81 | [7 empty] | 0 |  |  | 0 | 0
C.2.6 | Nose Plate (Front of Car) | Connor Archer | Low | 1 | Protective panel that goes on the front face of the car |  | Fabricate | Corrugated Plastic | 0.89 | 0.89 |  |  |  | 0 | 1 | 1 | 0 | 1 |  |  | 0 | 0 | No
C.2.7 | Nose Skid Plate | Justin Moyer | Low | 1 | Protective panel that goes underneath the nose of the car |  | Fabricate | aluminun sheet metal | 0.62 | 0.62 | OnlineMetals.com |  | Link | 0 | 1 | 1 | 0 | 1 | 23.64 |  | 23.64 | 23.64 | No
C.2.8 | Skid Plate | Justin Moyer | Low | 1 | Protective panel that goes underneath the cockpit of the car |  | Fabricate | aluminun sheet metal | 0.93 | 0.93 | OnlineMetals.com |  | Link | 0 | 1 | 1 | 0 | 1 | 81.39 |  | 81.39 | 81.39 | No
C.2.9 | Rear Skid Plate | Justin Moyer | Low | 1 | Protective panel that goes underneath the rear of the car |  | Fabricate | aluminun sheet metal |  | 0 | [7 empty] | 0 |  |  | 0 | 0
C.2.10 | Hood | Connor Archer | Low | 1 | Semi-protective panel on top of the nose of the car |  | Fabricate | Corrugated plastic | 0.74 | 0.74 |  |  |  |  | 1 | 1 |  | 1 |  |  | 0 | 0
C.3 | Ergonomics | Jacob Tasker | [7 empty] | N/A |  |  |  |  | 1 | 1 | 0 | 1 | 450 |  | 0 | 450
C.3.1 | Seat | Coby Brown | Low | 1 | Seat |  | Fabricate |  | 4 | 4 |  |  |  | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | No
C.3.2 | Seat Cushioning | Coby Brown | Low | 1 | Padding |  | Fabricate |  | 1 | 1 |  |  |  |  | 1 |  |  | 0 |  |  | 0 | 0 | No
C.4 | Firewall | Justin Moyer | Medium | 1 | Panel attached to rear roll hoop that protects the driver from fire |  | Fabricate | aluminun sheet metal | 2.61 | 2.61 | Home Depot |  | Link | 0 | 1 | 1 | 0 | 2 | 26.52 | 0 | 53.04 | 53.04 | No
C.4.1 | Firewall Plate | [8 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0 | No
C.4.2 | Seat Belt Cover | [8 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0 | No
C.5 | Mounts | Micah Burkhart | High | [5 empty] | 15 | 15 | [7 empty] | 0 |  |  | 0 | 0
C.5.1 | Engine Mounts | Aaron Brooks | Med | 2 | Tabs that connect to the rear Diff to hold the Engine. |  | Fabricate |  |  | 0 | McMaster Carr | 4459T288 | 4459T287 |  | 1 | 1 |  | 1 |  |  | 0 | 0 | No | No
C.5.2 | Differential Mounts | Aaron Brooks | High | 2 | Semi-circle mounts to hold the Rear Differantial in place |  | Fabricate |  |  | 0 | McMaster Carr | 4459T289 | 4459T288 |  | 1 | 1 |  | 1 |  |  | 0 | 0 | No | No
C.5.3.1 | Shock Mounts Rear | Aaron Brooks | Low |  |  |  | Fabricate |  |  | 0 | McMaster Carr | 4459T290 | 4459T289 |  | 1 | 1 |  | 1 |  |  | 0 | 0 | No
C.5.3.2 | Shock Mounts Front | [8 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0 | No
C.5.4 | Seat Mounts | [8 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0 | No
0
0
0
0
0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0 | No
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  |  | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [7 empty] | 0 |  |  | 0 | 0

## Suspension
Add Parts Under each componente by adding a .X to it | [12 empty] | Paste A link here as link
Total overall Cost: | 2658.97 | Total Weight (lb): | 130.2683 | # of Parts on Car: | 60.8841
2649.02
# | Part Name | Owner | Design Effort (Low, Med, High) | QTY Nessary for Car | General Description | Same as (# that is the same part) | Fabricate or Off the Shelf | Material | Mass/part (lb) | Mass Total (lb) On Car | Supplier | Part # | Link | Price/part | # of Spare Parts | Parts Per Package | # of Packages or Parts | # of Spare Parts or Packages | Total # of Parts or Packages to Order | Price per Package or Part | Shipping Cost | Cost Without Spare Parts | Total Cost | Ordered | Received |  | Cost Breakdown
S.1 | Front Suspension Arms | [8 empty] | 0 | [11 empty] | 0 | 0
S1.0.1 | Grease Zerk | Beau | High | 8 | Zerk where grease will be inserted into the bushing assembly, mounted on the arms, (size) | n/a | Off the shelf | Zinc Coated Steel |  | 0 |  |  |  |  | 2 | 10 | 1 | 0 | 1 |  |  | 0 | 0 |  | Yes
S1.0.2 | Bushing | Beau | Med | 16 | Custom Bushing 1" OD | n/a | Fabricate | Nylon |  | 0 | Already have material | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1.0.3 | Bushing Sleeve | Beau | Low | 8 | Bushing Sleeve 5/8" OD x .12" Wall |  | Fabricate | 4130 Steel |  | 0 | [6 empty] | 1 | 0 | 1 |  |  | 0 | 0
S.1.1 | Upper A-arm | Beau | Med | 2 | 4.34ft. of 1" OD x 0.035" Wall Tubing per arm | Secondary Members | Fabricate | 4130 Steel | 1.52 | 3.04 | McMaster-Carr | 89955K339 | A-Arms | 100 | 0 | 1 | 2 | 0 | 2 | 100 |  | 200 | 200 |  |  | Arms | 200
S.1.2 | Lower A-arm | Beau | Med | 2 | 4.24ft. of 1" OD x 0.035" Wall Tubing per arm | Secondary Members | Fabricate | 4130 Steel | 1.85 | 3.7 | McMaster-Carr | 89955K339 | A-Arms |  | 0 | 1 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | Shocks | 1424
S.1.3 | Front Shocks | Chancey | Med | 2 |  | n/a | Off the shelf | Aluminum | 5 | 10 | Filthy Motorsports |  |  | 356 | 0 | 1 | 2 | 0 | 2 | 356 | 0 | 712 | 712 |  |  | Limiting Gear | 50
S.1.3.1 | Limit Straps | Chancey | Low | 4 | 1" Wide Blue 25' Length | 3510T81 | Off the Shelf | Nylon | 0.2 | 0.8 | McMaster-Carr | 3510T81 | HYPERLINK(https://www.mcmaster.com/3510T82/,Limit Straps) | 26.5 | 0 | 1 | 1 | 0 | 1 | 26.5 |  | 26.5 | 26.5 |  |  | Knuckles | 370
S.1.3.2 | Bump Stops | Chancey | Low | 4 | 1.25 Shaft |  |  |  | 0.1 | 0.4 | [8 empty] | 0 |  |  | 0 | 0 |  |  | Hubs | 167
S.2 | Swing Arm |  |  | 2 |  |  |  |  | 4.5 | 9 | [8 empty] | 0 |  |  | 0 | 0 |  |  | Total | 2211
S.2.1 | Parallel Arms |  |  | 4 |  |  |  |  | 1.5 | 6 | [8 empty] | 0 |  |  | 0 | 0
S.2.1.1 | Bungs |  |  | 14 |  |  |  |  | 0.2 | 2.8 | [8 empty] | 0 |  |  | 0 | 0
S.2.1.2 | Ball Joints |  |  | 10 |  |  |  |  | 0.25 | 2.5 | [8 empty] | 0 |  |  | 0 | 0
S.2.2 | Rear Shocks |  |  | 2 |  |  |  |  | 5 | 10 |  |  |  | 356 | 0 | 1 | 2 | 0 | 2 | 356 | 0 | 712 | 712
S.3 | Knuckle | [8 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
S.3.1 | Front Knuckle | Matthew | High | 2 | CNC Cut, 6061 Aluminum (4" x 6" x 8") Bars | n/a | Fabricated | 6061 Aluminum | 1.8 | 3.6 | Midwest Steel & Aluminum | 61AFB46 | Front Knuckle | 81.01 | 0 | 1 | 2 | 0 | 2 | 81.01 | 23.16 | 185.18 | 185.18 | No | No
S.3.1.1 | Ball Joints | Matthew | Med | 4 |  | n/a | Off the shelf |  | 0.25 | 1 |  |  |  |  | 1 | 1 | 4 | 1 | 5 | 9.95 | 9.95 | 49.75 | 59.7 | No | No
S.3.2 | Rear Knuckle | Danny | High | 2 | CNC Cut, 6061 Aluminum (4" x 6" x 8") Bars | Front Knuckle | Fabricated | 6061 Aluminum | 2.5 | 5 | Midwest Steel & Aluminum | 61AFB46 | Rear Knuckle | 81.01 | 0 | 1 | 2 | 0 | 2 | 81.01 | 23.16 | 185.18 | 185.18 | No | No
S.4 | Wheels |  |  | 4 |  |  |  |  | 0 | 0 | [8 empty] | 0 |  |  | 0 | 0
S.4.1 | Hubs |  |  | 4 | CNC Cut, 7075 Aluminum (5" x 6" x 6") Bars |  |  |  |  | 0 | [8 empty] | 0 |  |  | 0 | 0
S.4.1.1 | Front Hubs | Jay | High | 2 | CNC Cut, 7075 Aluminum (5" x 6" x 6") Bars | 4.1.2 (rear hubs) | Fabricated | 7075 Aluminum | 1.8 | 3.6 | Midwest Steel & Aluminum | (61AFB38)? | Front Hubs | 128.84 | 0 | 1 | 2 | 0 | 2 | 128.84 | 31.525 | 289.205 | 289.205 | No | No
S.4.1.2 | Rear Hubs | Jay | High | 2 | CNC Cut, 7075 Aluminum (5" x 6" x 6") Bars | 4.1.1(front hubs) | Fabricated | 7075 Aluminum | 1.8 | 3.6 | Midwest Steel & Aluminum | (61AFB38)? | Rear hubs | 128.84 | 0 | 1 | 2 | 0 | 2 | 128.84 | 31.525 | 289.205 | 289.205 | No | No
S.4.2 | Sprag Clutch Bearings | Jay | Low | 2 | Ball and Roller Bearing, Sprag Clutch Unit (25mm, 58mm, 34mm) |  | Off the shelf | Steel? | 1.0141 | 2.0283 | GMN Bearing USA | FND 453 M | Sprag Clutch | 0 | 2 | 4 | 1 | 0 | 4 | 0 |  | 0 | 0 | No | No
S.4.3 | Rims | Chancey |  | 4 | [5 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
S.4.3.1 | Front Rims |  |  | 2 |  |  |  |  | 3 | 6 | [8 empty] | 0 |  |  | 0 | 0
S.4.3.2 | Rear Rims |  |  | 2 |  |  |  |  | 3 | 6 | [8 empty] | 0 |  |  | 0 | 0
S.4.4 | Tires |  |  | 4 | [5 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
S.4.4.1 | Front Tires | Chancey | Med | 2 | 23x7x10 ASTROAY OES FRONT ATV TIRE | n/a | Off the shelf | Rubber | 12.8 | 25.6 | Chapprol |  | Front Tires |  | 1 | 1 | 2 | 1 | 3 |  | 0 | 0 | 0 | No | No
S.4.4.2 | Rear Tires | Chancey |  | 2 |  |  |  |  | 12.8 | 25.6 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0

## Driver Controls
Add Parts Under each componente by adding a .X to it | [6 empty] | Steering | Brakes | Electrical | Safety |  |  | Paste A link here as link
[7 empty] | 567.23 | 787.98 | 363.36 | 573.98
Total overall Cost: | 2292.55 | Total Weight (lbs): | 30.29 | # of Parts on Car: | 56
2114.37
# | Part Name | Owner | Design Effort (Low, Med, High) | QTY Nessary for Car | General Description | Same as (# that is the same part) | Fabricate or Off the Shelf | Material | Mass/part (lb) | Mass Total (lb) On Car | Supplier | Part # | Link | Price/part | # of Spare Parts | Parts Per Package | # of Packages or Parts | # of Spare Parts or Packages | Total # of Parts or Packages to Order | Price per Package or Part | Shipping Cost | Cost Without Spare Parts | Total Cost | Ordered | Received
DC.1 | Steering | [17 empty] | 0 |  |  | 0 | 0
DC.1.1 | Tie Rod Kit | Nathanael | High | 2 | Connects rack to steering arm |  | Off the Shelf | Steel | 1 | 2 | CIP1 | C13-3145 | TieRodKit | 34.195 |  | 2 | 1 | 1 | 2 | 68.39 | 0 | 68.39 | 136.78
DC.1.1.1 | Heim Joints | Ryan | Low | 2 | Flexible connector for tie rods |  | Off the Shelf | Alloy Steel | 0.3 | 0.6 | McMaster-Carr | 6960T43 | TREnd | 13.74 |  | 1 | 2 | 0 | 2 | 13.74 | 0 | 27.48 | 27.48
DC.1.2 | Rack & Pinion | Casey | Med | 1 | Moves left and right for steering |  | Off the Shelf | Steel? | 1.9 | 1.9 | Joes's Racing | 57100 | Rack | 367.95 |  | 1 | 1 | 0 | 1 | 367.95 | 0 | 367.95 | 367.95
DC.1.3 | Steering Column | Casey | Med | 1 | Connects steering wheel to rack |  | Off the Shelf | Aluminum | 1.05 | 1.05 | onlinemetals.com |  | steering column | 19.07 |  | 1 | 1 | 0 | 1 | 19.07 | 0 | 19.07 | 19.07
DC.1.3.2.1 | Coupler | Nathanael | Med | 1 | Connects steering column to rack |  | Off the Shelf | Steel probably | 0.29 | 0.29 | amazon | ‎310-240 | Coupler | 15.95 |  | 1 | 1 | 0 | 1 | 15.95 | 0 | 0 | 15.95
DC.1.4 | Steering Wheel | Casey | High | 1 | Allows the driver to turn |  | Fabricate | Aluminum/PLA | ? | ? | N/A | N/A | N/A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DC.2 | Brakes | [17 empty] | 0 |  |  | 0 | 0
DC.2.1 | Master Cylinder | Bryan | low | 2 | Pressure for system |  | Off the Shelf | Aluminum | 1.7 | 3.4 | Wilwood | 260-15088 | MC | 65.4 |  | 1 | 2 | 0 | 2 | 65.4 | 0 | 130.8 | 130.8
DC.2.2 | Remote resovoir | Bryan | Low | 2 | Hold excess Brake fluid |  | Off the Shelf | Plastic/Rubber |  | 0 | Wilwood | 260-7577 | Resevoir | 54.84 |  | 1 | 2 | 0 | 2 | 54.84 | 0 | 109.68 | 109.68
DC.2.2.1 | Soft Line | Bryan | Low | 4 | Transports brake fluid |  | Off the Shelf | Braided Steel | 0.1 | 0.4 | Wilwood | 220-7686 | Soft line | 24.61 |  | 1 | 4 | 0 | 4 | 24.61 | 0 | 98.44 | 98.44
DC.2.2.2 | Hard Line | Bryan | Low | 1 | 3/16 Inch Copper Brake line |  | Off the shelf (We own) | Copper | 0.5 | 0.5 | Amazon | ‎MUBRAKE-KITGD316 | Hard line | 13.98 |  | 1 | 1 | 0 | 1 | 13.98 | 0 | 13.98 | 13.98
DC.2.2.3 | Tee Fitting | Bryan | Low | 2 | Diverts brake fluid to brake pressure switch |  | Off the Shelf | Brass | 0.05 | 0.1 | Summit Racing | ALL50137 | Tee fitting | 8.99 |  | 1 | 2 | 2 | 4 | 8.99 | 0 | 17.98 | 35.96
DC.2.3 | Front Rotors | Bryan | Med | 2 | Steel (exploring aluminum) Brake Rotor |  | Fabricate | Steel Alloy/ or Aluminium | 0.35 | 0.7 | [5 empty] | 1 | 2 | 0 | 0 |  | 0 | 0 | 0
DC.2.4 | Front Calipers | Bryan | Med | 2 |  |  | Off the Shelf | Steel Alloy/ or Aluminium |  | 0 | Wilwood |  | Calipers | 219.72 |  | 1 | 1 | 0 | 1 | 219.72 | 0 | 219.72 | 219.72
DC.2.5 | Rear Rotors | Bryan | Med | 2 | Steel (exploring aluminum) Brake Rotor | 2.3 | Fabricate | Steel Alloy | 0.35 | 0.7 | [5 empty] | 1 | 2 | 0 | 0 |  | 0 | 0 | 0
DC.2.6 | Rear Calipers | Bryan | Med | 2 |  |  | Off the Shelf | Aluminum | 1.4 | 2.8 | Wilwood |  | Calipers |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DC 2.7 | Brake Pedal | Bryan | Low | 1 | Floor it to stop |  | Off the shelf | Aluminum | 3 | 3 | Wilwood | 340-12509 | Brake pedal | 149.88 |  | 1 | 1 | 0 | 1 | 149.88 | 29.52 | 179.4 | 179.4
DC.3 | Electrical | [8 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
DC.3.1 | Kill Switches | Titus | Low | 2 | Turns off engine |  | Off the Shelf | Plastic | 0.1 | 0.2 | MFGSupply | 01-171 | Kill Switch | 32.49 |  | 1 | 2 | 0 | 2 | 32.49 | 6.99 | 71.97 | 71.97
DC.3.2.1 | Brake Light | Titus | Low | 1 | Turns on when car brakes |  | Off the Shelf | Plastic | 0.25 | 0.7 | Amazon | 2411450 | Brake Light | 49.99 |  | 1 | 1 | 0 | 1 | 49.99 | 0 | 49.99 | 49.99
| Brake Switch | [8 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
DC.3.4 | Reverse Components | [8 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
DC.3.4.1 | Reverse Light | Titus | Low | 1 | MOTOKU Rear Left and Right Brake Tail Light for Polaris Sportsman |  | Off the Shelf | Plastic | 0.25 | 0.25 | Amazon | TBL6110-WH | Reverse Light | 11.95 |  | 1 | 1 | 0 | 1 | 11.95 | 0 | 11.95 | 11.95
DC.3.4.2 | Reverse Alarm | Titus | Low | 1 | Backup Sound Alarm for Pickup Truck [112dB] |  | Off the Shelf | Plastic | 0.5 | 0.5 | Amazon | SABA20 | Reverse Alarm | 29.99 |  | 1 | 1 | 0 | 1 | 29.99 | 0 | 29.99 | 29.99
DC.3.5 | Front Diff Switch | Titus | Low | 1 | Controls power to front diff |  | Off the Shelf | Plastic | 0.1 | 0.1 | Amazon | 4333807067 | Front Diff Switch | 9.99 |  | 1 | 1 | 0 | 1 | 9.99 |  | 9.99 | 9.99
DC.3.7 | Battery | Titus | Low | 1 | Li-Ion battery |  | Off the Shelf | Lithium-Ion | 1 | 1 | Amazon | YB1206000 | Battery | 31.99 |  | 1 | 1 | 0 | 1 | 31.99 | 0 | 31.99 | 31.99
DC.3.7.1 | Battery Box | Titus | Low | 1 | Waterproof casing for battery components |  | Fabricate | Plastic | 0.6 | 0.6 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
DC.3.8.1 | Power Distribution Block | Titus | Low | 1 | PCB007 1X 12 Position Power Distribution Board |  | Off the Shelf | PCB | 0 | 0 | Amazon | B07DW2C4ZB | Power Distrib | 6.99 |  | 1 | 1 | 0 | 1 | 6.99 | 0 | 6.99 | 6.99
DC.3.8.2 | Wires | Titus | Low | 1 | InstallGear 16 Gauge AWG Speaker Wire |  | Off the Shelf |  | 0 | 0 | Amazon | ‎ IG16100RBSW | Wires | 14.99 |  | 1 | 1 | 0 | 1 | 14.99 | 0 | 14.99 | 14.99
DC.3.8.3 | Wire Connectors | Titus | Low | 4 | Nilight - 50020R 2Pin Way 16AWG Waterproof Wire |  | Off the Shelf | Wire | 0 | 0 | Amazon | 50020R | Wire Connectors | 10.52 |  | 10 | 1 | 0 | 1 | 10.52 | 0 | 10.52 | 10.52
DC.3.8.4 | Battery Connector | Titus | Low | 1 | CERRXIAN DC5521 Power Pigtails Cable |  | Off the Shelf | Wire | 0 | 0 | Amazon | B0BNPXN8RD | Battery Connector | 9.99 |  | 2 | 1 | 0 | 1 | 8.99 | 0 | 8.99 | 8.99
DC.3.10 | Transponder Subscription | Titus | Low | 1 | Used for tracking the car for the purpose of timing and scoring |  | Owned | Plastic | 0.5 | 0.5 | MyLaps | X2 | Transponder | 115.99 |  | 1 | 1 | 0 | 1 | 115.99 | 0 | 0 | 115.99
DC.4 | Safety | [8 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
DC.4.1 | Harness | Oriana | Low | 1 | Simpson Latch and Link Driver Restraint System |  | Off the Shelf | Polyester | 5.1 | 5.1 | Summit Racing | 29043BK | Harness | 124.95 |  | 1 | 1 | 0 | 1 | 124.95 | 0 | 124.95 | 124.95
DC.4.2 | Arm Restraints | Lauren | Low | 1 | G-FORCE Arm Restraints |  | Off the Shelf | Polyester | 0 | 0 | Summit Racing | 4087ADUBK | Arm Restraints | 41 |  | 2 | 1 | 0 | 1 | 41 |  | 41 | 41
DC.4.3 | Helmet | Lauren | Low | 1 | Large Thor 2022 Sector Helmet |  | Off the Shelf | Polycarbonate | 0 | 0 | MotoSport | 1105571 | Helmet | 99.95 |  | 1 | 1 | 0 | 1 | 99.95 | 0 | 99.95 | 99.95
DC.4.4.1 | Fire Resistant Shirt | Lauren | Low | 1 | RaceQuip Fire Resistant Shirt | N/A | Off the Shelf | Plastic | 0 | 0 | Amazon | B088D6LZFY | Fire Resistant Shirt | 61.16 |  | 1 | 1 | 0 | 0 | 61.16 | 0 | 61.16 | 0
DC.4.4.2 | Fire Resistant Pants | Lauren | Low | 1 | Titicana's Men's Fire Resistant Cargo Pants (32x32 & 34x34) | N/A | Off the Shelf | Cotton | 0 | 0 | Amazon | B07VJNK3RG | Titicaca Men's FR Cargo Pants Flame Resistant Pants Lightweight 7.5oz 100% Cotton Navy Fire Retardant Elastic Waist Pants at Amazon Men’s Clothing store | 45.99 |  | 1 | 2 | 0 | 2 | 45.99 | 0 | 91.98 | 91.98
DC.4.4.3 | Gloves | Lauren | Low | 1 | Driver equipment |  | Off the Shelf | Synthetic Leather | 0 | 0 | Amazon | B0C2TKL4YB | Gloves | 0 |  | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0
DC.4.5 | Goggles | Lauren | Low | 1 | Driver eye protection | N/A | Off the Shelf | Plastic |  | 0 | Amazon | B0CKWFRV94 | Goggles | 26.25 |  | 1 | 1 | 0 | 1 | 26.25 | 0 | 26.25 | 26.25
DC.4.5.1 | Goggle Lens Strips | Lauren | Low | 1 | Goggles accesory |  | Off the Shelf |  |  | 0 | Amazon | ‎59085-00001 | Tear Off Strips | 28.81 |  | 50 | 1 | 0 | 1 | 28.81 |  | 28.81 | 28.81
DC.4.6 | Fire Extinguisher | Lauren | Low | 1 | Kiddle Fire Extiguisher 2 pack |  | Off the Shelf | Aluminum | 3.9 | 3.9 | Amazon | ‎21032640 | Fire Extinguisher | 21.03 |  | 1 | 1 | 1 | 2 | 21.03 | 0 | 21.03 | 42.06
DC.4.6.1 | Fire Extinguisher Mount | Lauren | Low | 1 | DV8 Off-Road Universal Fire Extingusiher Mount |  | Already own | Aluminum | 0 | 0 | DV8 Off-Road | SKU D-FIREX-MNT-DOR | FE Mount | 86.99 |  | 1 | 1 | 0 | 1 | 86.99 | 0 | 86.99 | 86.99
DC.4.7 | Neck Guard | Lauren | Low | 1 | Neck support | N/A | Off the Shelf |  |  | 0 | N/A | N/A | N/A | 31.99 |  | 1 | 1 | 0 | 1 | 31.99 | 0 | 31.99 | 31.99
DC.4.8 | Head Restraint | Lauren | Low | 1 | Head rest for driver |  | Fabricate | Wood, Fabric |  | 0 | N/A | N/A | N/A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0
[10 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0

## Tools&Shop Supplies
Part Number | Part Name | QTY | General Description | Material | Mass/part (g) | Mass Total (g) | Supplier | Part # | Link | Price/part | Total # of Parts | Total Cost | Bought | Received
TS-01 | Wire Stripper/Crimper | 1 | Strip and crimp wires | Steel | Not specified | Not specified | Home Depot | Not specified | https://www.homedepot.com/p/Klein-Tools-Klein-Kurve-Wire-Stripper-Crimper-Cutter-Multi-Tool-1019SEN/305303655?source=shoppingads&locale=en-US&srsltid=AR5OiO3suyEpjNGk0Drg-PPRgdg0q2Rpjg1O17e-LPtnTjpunzyHD2TWrJk |  | 1 |  | no | no
TS-02 | Label Maker? | [11 empty] | no | no
TS-03 | Cutting Wheels (15 pack) | 1 | For cutting metal | Aluminum oxide blend | Not specified | Not specified | Home Depot | Not specified | https://www.homedepot.com/p/DIABLO-4-1-2-in-x-0-040-in-x-7-8-in-Thin-Kerf-Metal-Cut-Off-Disc-15-Pack-DBD045040115F/301454108 |  | 1 |  | yes | yes
| White paint markers | [7 empty] | https://www.amazon.com/gp/product/B08NWK73ZN/ref=ox_sc_saved_image_8?smid=A5AEPW9TWZ5E5&psc=1 |  |  |  | yes | yes
| calipers | [7 empty] | https://www.amazon.com/gp/product/B08DLQP1T6/ref=ox_sc_saved_image_6?smid=A2KH7CPIYV4PJT&psc=1 |  |  |  | No | No
| tachometer | [7 empty] | https://www.amazon.com/gp/product/B000I5LDVC/ref=ox_sc_saved_image_5?smid=ATVPDKIKX0DER&psc=1 |  |  |  | No | No
| grommets | [7 empty] | https://www.amazon.com/125pc-Sizes-Rubber-Grommet-Kit/dp/B01NAN025Y/ref=sr_1_4?crid=17UECRBQ3P8AJ&keywords=grommet+set&qid=1698954852&sprefix=grommet+set%2Caps%2C94&sr=8-4
| mig .023-.030 liner | 1 | proper liner for smaller wire size |  |  |  | amazon | LM1A-10 | https://www.amazon.com/gp/product/B07QZ4KW32/ref=ox_sc_act_title_1?smid=AFCC0L7419CQ6&th=1 | 28.99 | 1 | 28.99
| mig .023-.025 contact tip | 1 | proper contract tip for smaller wire 10 pack |  |  |  | amazon | T-M023 | https://www.amazon.com/gp/product/B07R2CG5CS/ref=ox_sc_act_title_3?smid=AE7O423127VC2&th=1 | 23.45 | 1 | 23.45
| mig .030 contact tip |  | contact tip for .030 wire 10 pack |  |  |  | amazon | T-M030 | https://www.amazon.com/gp/product/B07R3CK8TJ/ref=ox_sc_act_title_2?smid=A3AFUUPS3VQPQ2&th=1 | 22.35 | 1 | 22.35
| mig .023 wire | 1 | .023 welding wire for thin metal |  |  |  | amazon | ‎23022 | https://www.amazon.com/Eastwood-Bronze-Copper-Welding-Fabrication/dp/B08FTJ9ZDQ/ref=sr_1_7?crid=37XT6G2QQ54E6&keywords=023+mig+welding+wire&qid=1701111779&refinements=p_36%3A1253528011&rnid=1243644011&s=hi&sprefix=023+mig+welding+wire%2Caps%2C87&sr=1-7 | 19.79 | 1 | 19.79 | yes | yes
| 1.25" hole saw | 3 | For cutting metal | N/A | N/A | N/A | lowes | 4977482 | 1.25" bit | 11.98 | 3 |  | yes | yes
| 1" hole saw | 3 | For cutting metal | N/A | N/A | N/A | lowes | 4977480 | 1" bit | 10.98 | 3 |  | yes | yes
| Aluminum flap disc | 1 | For cutting metal | N/A | N/A | N/A | lowes | B07P5Q1R22 | Flap disks | 19.99 | 1 |  | yes | yes
| PipeMaster 1" | 1 | For cutting metal | N/A | N/A | N/A | lowes | P-T100 | 1" PipeMaster | 46.2 | 1 |  | yes | yes
| PipeMaster 1.25" | 1 | For cutting metal | N/A | N/A | N/A | lowes | P-T125 | 1.25" PipeMaster | 48.04 | 1 |  | yes | yes
[13 empty] | no | no
[13 empty] | no | no

## Fasteners
TEAM PO#: |  | #01 |  | EXAMPLE
TEAM LEAD NAME/EMAIL:
TEAM | SUBTEAM | PART NAME | PART NUMBER | PART DESCRIPTION (URL) | VENDOR | Availability / Est. ship date ? | Shipping Method | Min. Order Qty / $$ ? | QUANTITY | PRICE | Shipping Cost | TOTAL | JUSTIFICATION
BAJA | Drivetrain | Gas Tank Mounting Bolt | 92865A855 | https://www.mcmaster.com/92865A849/ | McMaster Car |  |  | 1 | 4 | 2.48 |  | 9.92 | Mount Gas tank
BAJA | Drivetrain | Gas Tank Rubber Washers | 94733A723 | https://www.mcmaster.com/94733A723/ | McMaster Car |  |  | 50 | 1 | 13.01 |  | 13.01 | Required by rules
BAJA | Drivetrain | Gas Tank Metal Washers | 91083A031 | https://www.mcmaster.com/91083A031/ | McMaster Car |  |  | 140 | 1 | 8.85 |  | 8.85 | Required by rules
BAJA | Drivetrain | Gas Tank Mounting Nut | 95615A270 | https://www.mcmaster.com/95615A270/ | McMaster Car |  |  | 10 | 1 | 10.5 |  | 10.5 | Mount gas tank
BAJA | Drivetrain | Engine Bolt | 90409A143 | https://www.mcmaster.com/90409A143/ | McMaster Car |  |  | 10 | 1 | 9.27 |  | 9.27 | Mount Engine
BAJA | Drivetrain | Engine Washer | 98023A032 | https://www.mcmaster.com/98023A032/ | McMaster Car |  |  | 25 | 1 | 8.98 |  | 8.98 | Mount Engine
BAJA | Drivetrain | Engine Rubber Washer | 90131A104 | https://www.mcmaster.com/90131A104/ | McMaster Car |  |  | 10 | 1 | 4.97 |  | 4.97 | Required by rules
BAJA | Drivetrain | Engine Nut | 97135A240 | https://www.mcmaster.com/97135A240/ | McMaster Car |  |  | 10 | 1 | 4.8 |  | 4.8 | Mount engine
BAJA | Drivetrain | Front diff bolt 3/8 -24
BAJA | Driver Controls | Kill Switch Bolt | 92865A624 | https://www.mcmaster.com/92865A624/ | McMaster-Carr |  |  | 50 | 1 | 13.84 |  | 13.84 | Mount killswitch
BAJA | Driver Controls | Kill Switch Nut | 95615A105 | https://www.mcmaster.com/92865A624/ | McMaster-Carr |  |  | 100 | 1 | 16.03 |  | 16.03 | Mount killswitch
|  | TOTAL | [9 empty] | 100.17